# Smart Oila Kids - 6 Week Roadmap

Generated: March 12, 2026 | Planning window: March 16, 2026 to April 26, 2026

Assumption: execution starts on Monday, March 16, 2026, using the current repo as the source of truth.

Source basis: Repo scan across App, Core, Features, Shared, and SmartOilaKidsTests; Planning docs: CHILD_ONLY_EXTRACTION_SPEC.md and PARENT_CHILD_TESTING.md; Release artifacts under output/doc/; Current checks run on March 12, 2026: child OpenAPI baseline PASS (REST 24/85, WS 8/23), parent-gap budget PASS (REST gap 60, WS gap 15), script tests PASS (22/22)

# 1. Current Repo Baseline

The app is already beyond a thin MVP. The repo ships auth, dashboard, chat, tasks, settings, geo background service, push routing, app lock flows, media recording/streaming coordinators, diagnostics, and EN/RU/UZ localization.

Navigation is DSN-gated: no DSN enters Auth; an existing DSN enters Main. Root lifecycle wiring starts geo, lock, media, and push sync services off the same session state.

Settings are not just cosmetic. They already include connected-device rename, avatar upload, delete/unlink flows, permissions center, diagnostics, app lock setup, media history, invite sharing, and LocalAuthentication-based protection.

Operational guardrails already exist in-repo: OpenAPI coverage/parity scripts, localization parity checks, release-readiness scripts, simulator smoke scripts, and a real-device validation matrix template.

The current roadmap should therefore focus on production hardening, contract closure, and release readiness - not rebuilding basic screens that are already implemented.

# 2. Architecture Constraints and Planning Signals

SwiftUI app with service-driven feature modules plus several singleton coordinators (geo, lock, media, push). Changes in DSN/session lifecycle can regress multiple features at once.

Background-sensitive features depend on iOS-only capabilities: CoreLocation background updates, APNs, ReplayKit, FamilyControls, ManagedSettings, DeviceActivity, and app-group backed extensions.

Screen Time code exists, but the default Info.plist flag SMARTOILA_SCREEN_TIME_FEATURES_ENABLED is currently false. Real validation needs a build/config path that enables the feature.

Parent-child integration tooling assumes the sibling parent repo exists at ../Smart Oila Parent and is buildable from the shared workspace.

The February extraction spec excludes some media/control surfaces, but the current repo already contains those modules. This roadmap assumes shipped code remains in scope unless product explicitly cuts it.

API coverage is improving but still selective. As of March 12, the child app covers 24 of 85 REST operations and 8 of 23 websocket routes; the largest remaining domains are members and devices.

# 3. Milestones

Milestone 1: Baseline, scope, and environment freeze completed with owner-assigned backlog for all child-critical gaps.

Milestone 2: Real-device validation completed for APNs, geo, Screen Time/app lock, and media command flows.

Milestone 3: Child-critical API/websocket gaps closed or explicitly de-scoped, with tighter OpenAPI baseline thresholds.

Milestone 4: Release candidate package ready with green gates, rollback plan, and pilot sign-off.

# 4. Week-by-Week Plan

| Week | Milestone | Weekly Goals | Deliverables | Key Dependencies | Key Risks |
| --- | --- | --- | --- | --- | --- |
| Week 1 Mar 16-22 | Freeze Baseline | Refresh repo-derived source-of-truth docs and align them with the shipped codebase, not the older extraction-only scope. Review members/devices OpenAPI gaps and tag each child-relevant route as build, validate, or explicitly out-of-scope. Lock the production environment checklist for API bases, websocket bases, token rules, APNs, and Screen Time feature enablement. | Updated roadmap package and refreshed child gap report Owner-assigned backlog for child-critical members/devices gaps Environment and entitlement checklist signed off by iOS + backend | Backend owner, OpenAPI specs, parent repo access, product decision on media/control in-scope status | Contract drift or scope confusion can waste the first 2 weeks; mitigate by freezing one repo-backed backlog |
| Week 2 Mar 23-29 | Real Device Validation | Execute the real-device matrix for APNs, background geo, lock-state convergence, logout/login edge cases, and media permission transitions. Validate Screen Time/app lock behavior on physical devices with the correct entitlements and feature flag enabled. Capture exact failure modes for ReplayKit, camera, microphone, and FamilyControls when the app is backgrounded, interrupted, or denied permissions. | Completed real-device validation matrix with pass/fail evidence Defect list ranked by release impact Entitlement and feature-flag decision log for Screen Time rollout | Physical iPhones, APNs-capable build, parent app test account, Screen Time entitlements | Simulator-only confidence is misleading; real-device issues may block geo, push, lock, or media flows late |
| Week 3 Mar 30-Apr 5 | Close Critical Contracts | Implement or verify the highest-value missing members/devices endpoints that unblock child flows, especially device/account/token/readback surfaces. Close any remaining child-side websocket gaps needed for app-lock/media/telemetry convergence. Re-run coverage after each batch and raise the baseline only after tested routes land. | Reduced child OpenAPI gap report with March 12 baseline improved Merged endpoint batch for child-critical gaps with integration notes Raised baseline thresholds in the child coverage gate once the batch is stable | Backend responses stable in staging/prod-like env, parent repo parity references, QA support for route validation | Fast route additions can create brittle decoding or auth assumptions; keep additions small and test-backed |
| Week 4 Apr 6-12 | Reliability Hardening | Soak-test chat reconnect, push deep-link routing, geo reconnect, lock recovery, and media transport under DSN switches and app lifecycle changes. Harden diagnostics so failures are visible in normal QA runs, not only in debug sessions. Fix stale-session, duplicate-delivery, and race-condition issues across the shared singleton coordinators. | 48-hour soak-test report Merged reliability fixes for DSN routing, reconnects, and lifecycle recovery Updated diagnostics checklist used by QA and release triage | Stable backend websocket environment, test accounts, long-running device access | Cross-feature regressions are likely because geo, lock, media, and push all key off the same session state |
| Week 5 Apr 13-19 | Polish and Sign-off Prep | Complete UX and localization review for settings protection, permissions guidance, diagnostics copy, and fallback/error states. Validate device-management flows end to end: rename, avatar upload, unlink, invite share, and media/app-lock settings surfaces. Prepare the release checklist package, including rollback criteria and pilot monitoring expectations. | QA/design review notes resolved Localization and copy sign-off for EN/RU/UZ Updated RC checklist and rollback plan package | Design/PM review, translation review, backend permissions on device-mutation endpoints | Late copy/layout issues can mask real logic defects; run full regression on the signed-off UI before RC |
| Week 6 Apr 20-26 | RC and Pilot Readiness | Run the full release-readiness stack: script tests, coverage gates, localization gates, simulator smoke, and the final real-device spot check. Cut the release candidate and assemble the sign-off bundle with evidence links, known issues, and rollback trigger thresholds. Start the pilot only if all Sev1/Sev2 issues are closed and all unresolved gaps are explicitly accepted. | Green release-readiness report Candidate build and sign-off packet Pilot monitoring checklist with owners and rollback triggers | Parent repo workspace, signing/build pipeline, backend freeze window, PM + QA + iOS approvals | Late backend contract changes or unresolved real-device defects can force a slip; keep a hard freeze and rollback path |

# 5. Explicit Dependencies

Backend/API owner support for child auth, members/devices route behavior, websocket route confirmation, and token rules

OpenAPI files at OpenAPI/rest_openapi.json and OpenAPI/ws_openapi.json remaining current and authoritative

Sibling parent repo available at ../Smart Oila Parent for workspace build, parity reference, and simulator smoke

Physical devices and APNs-ready builds for push, background geo, ReplayKit, and FamilyControls validation

Correct entitlements/configuration for app groups, usage-report and schedule-monitor extensions, and Screen Time feature enablement

Product/design agreement on which shipped but previously out-of-scope features remain in the child release

# 6. Explicit Risks

Screen Time and app-lock code may appear complete in source while still failing in production-like conditions if entitlements or feature flags are wrong.

APNs, background geo, ReplayKit, and FamilyControls behavior can diverge sharply between simulator and device, so late discovery is likely unless Week 2 happens on hardware.

Members/devices API gaps remain the biggest functional expansion risk; shipping without resolving child-critical ones keeps the app dependent on fallback behavior.

The app relies on shared singleton coordinators, so DSN/session bugs can surface as chat, push, geo, lock, and media issues simultaneously.

Parent-child integration depends on another repo and shared backend contracts; late upstream changes can invalidate a green local build.

# 7. Definition of Done by End of Week 6

All child-critical flows have passing evidence on real devices: auth, dashboard, chat, tasks, settings, geo, push, app lock, and any media/control features kept in scope.

The release-readiness scripts remain green and the OpenAPI baseline is tighter than the March 12 starting point.

All remaining API or websocket gaps are either closed, documented as accepted exclusions, or blocked on named external owners with sign-off.

The team has a signed RC checklist, rollback plan, and pilot monitoring owner list before rollout starts.