Smart Oila Parent + Child 6-Week Release Plan

Date: 2026-04-08
Scope: Parent app finish pass + child app release completion + shared integration hardening

This roadmap is based on the current repo state in /Users/jakhongirnematov/Desktop/Smart Oila Parent and /Users/jakhongirnematov/Desktop/Smart Oila Kids, plus the checked-in release docs and project structure. It assumes execution starts immediately on 2026-04-08.

# Current Starting Point

Child app: repo status is near-RC. The child-owned feature set is already implemented for auth/session, chat, tasks, geo, lock, app lock, usage-based limits, SOS, push, diagnostics, and media transport. Contract, localization, script, and XCTest gates are green in the checked-in release docs; remaining blockers are backend signoff and real-device validation.

Parent app: repo is buildable and already contains typed APIs and product-facing screens for applications, device lock, geofence, chat, recordings, profile, support, and push routing. The main remaining work is test coverage, legacy cleanup, release configuration hardening, and end-to-end validation with the child app.

Shared release path: both apps are expected to be tested together through SmartOilaSuite.xcworkspace while keeping SmartOilaKids.xcodeproj and SmartOilaParent.xcodeproj as the canonical checked-in projects.

# Architecture Constraints From The Repos

Child behavior depends on Screen Time extensions, Family Controls entitlements, and shared App Group state. Those paths cannot be fully validated in simulator-only testing.

Parent still carries Source/Legacy slices and active NetworkServiceLegacy usage in task flows. Refactoring without a real test lane is the highest regression risk in the parent repo.

Parent release configuration still shows external-release debt: NSAllowsArbitraryLoads is enabled, aps-environment is set to development, and secrets are still embedded in source/resources.

Cross-app features depend on backend decisions that are not purely client-owned: QR bind fallback policy, websocket v2 preference, push payload schema, APNs token semantics, and media task lifecycle behavior.

# Week-By-Week Plan

| Week | Dates | Weekly Goal / Milestone | Clear Deliverables |
| --- | --- | --- | --- |
| Week 1 | Apr 8-14 | Milestone 1: freeze the shared release baseline. Lock backend decisions for bind fallback, websocket v2, push payloads, and APNs semantics. Stand up the parent test lane before deeper refactors. | Published contract matrix; parent test target or equivalent automated smoke lane; named owners for parent, child, backend, QA, and release; updated parent-child real-device checklist. |
| Week 2 | Apr 15-21 | Milestone 2: finish parent hardening foundation. Move remaining must-ship parent flows away from workbench and legacy paths, close top-level UX gaps, and keep child readiness gates green. | Parent service hub and product navigation finalized for applications, lock, geofence, chat, recordings, profile, and support; active NetworkServiceLegacy dependency list reduced or explicitly deferred; child script/readiness checks still green. |
| Week 3 | Apr 22-28 | Milestone 3: complete parent-to-child control validation. Exercise applications, daily limits, manual lock, full-device lock schedule, geofence, and QR bind/session flows on paired real devices. | Signed-off real-device evidence for core control flows; defect list triaged and burned down; parent and child state stay consistent after retries, reconnects, and app relaunches. |
| Week 4 | Apr 29-May 5 | Milestone 4: stabilize realtime, push, and media. Harden push routing, chat refresh, SOS/removal/lock events, recordings, live stream states, and reconnect/background behavior. | Route-aware parent push UX for SOS, removal attempts, lock, task, and media events; shared realtime regression report; child diagnostics exported for push and media soak runs. |
| Week 5 | May 6-12 | Milestone 5: close release configuration and security debt. Externalize secrets, switch parent push config to production-ready settings, resolve or justify ATS exceptions, and run archive/distribution checks for both apps. | Release-config checklist completed; production entitlement review completed; archive evidence for parent and child; localization and release-build smoke results attached. |
| Week 6 | May 13-19 | Milestone 6: make the RC decision. Run full regression, complete rollback rehearsal, gather PM/backend/QA sign-off, and decide whether to cut release candidates or hold. | RC builds for both apps; final go/no-go sheet; rollback and support playbook; launch-day checklist and open-issues list with explicit owners. |

# Milestones

By 2026-04-14: shared contract choices, ownership, and test baseline are frozen.

By 2026-04-21: parent must-ship flows are on stable product paths instead of workbench-first or legacy-only paths.

By 2026-04-28: parent can control the child app end to end on real devices for the core safety/control feature set.

By 2026-05-05: realtime, push, chat, and media flows are stable under reconnect and background scenarios.

By 2026-05-12: release configuration, archives, and security cleanup are ready for an external release decision.

By 2026-05-19: release candidates are either approved or blocked with explicit ownership and recovery dates.

# Dependencies

Backend owner availability for bind-policy signoff, websocket routing decisions, push payload schema, APNs token handling, and media task semantics.

At least one paired parent-child real-device setup on an APNs-capable backend environment; simulator coverage is not enough for the final pass.

Access to both canonical Xcode projects plus the shared workspace for paired validation and archive checks.

Design/PM review for ambiguous Figma frames and for expectation alignment on iOS-only limitations.

Release owner access for signing, archive export, entitlement review, and App Store / distribution steps.

# Risks

Parent has no checked-in automated test target today. That raises the chance of regressions during legacy cleanup and service-hub refactors.

Child remaining blockers are manual and contractual rather than implementation gaps. Schedule slip risk is mostly tied to backend response time and real-device availability.

Screen Time, Family Controls, background geo cadence, APNs delivery, and lock enforcement cannot be fully proven in simulator-only runs.

Parent release debt can block external shipment even if features are complete: NSAllowsArbitraryLoads, development aps-environment, and embedded secrets must be resolved or formally accepted.

Shared push/location/lock/chat/media behavior can fail at integration boundaries even when each app looks healthy in isolation.

The Android-style uninstall or admin-removal prevention model referenced in backend materials is not available on App Store iOS, so PM/client scope alignment must stay explicit.

# Recommended Success Criteria

Parent and child both build, archive, and install from their canonical checked-in projects.

Parent control actions visibly propagate to the child on real devices with predictable retry and error handling.

Open critical issues at RC time are limited to documented release waivers, not unknown contract or environment behavior.

Repo inputs used: Smart Oila Kids README and release docs, Smart Oila Parent README and checked-in finish/execution docs, plus current project structure and resource files reviewed on 2026-04-08.