Smart Oila Parent + Child RC-Day Timeline

Date: 2026-04-08
Purpose: release-day timeline and war-room plan for the combined parent-child RC decision window

This timeline assumes the release is still HOLD before the window opens. The window only proceeds if the preflight gates are green, the shared real-device evidence is complete, and the current blocker tracker does not contain an open Sev1 blocker.

# Before The Window Opens

Confirm the combined RC checklist, blocker tracker, handoff note, and evidence-pack template are all open and current.

Confirm the paired parent-child devices, backend account, DSN, and APNs-capable environment are available.

Confirm the release owner knows where archive timestamps, organizer screenshots, and diagnostics exports will be stored.

# War-Room Roles

| Role | Primary Responsibility | When They Must Be Present |
| --- | --- | --- |
| PM | Owns release decision, waivers, and communication on GO / HOLD / NO-GO. | Start of window, final sign-off, and any scope dispute. |
| iOS Lead | Owns build sanity, archives, code-level triage, and technical go/no-go advice. | Entire window. |
| QA Lead | Owns paired-device execution, evidence completeness, and fail / retry calls. | Entire validation and sign-off window. |
| Backend Lead | Answers contract, payload, environment, and push/media behavior questions. | Preflight plus any contract or environment issue. |
| Release Owner | Owns archive/Organizer steps, evidence pack assembly, and final release recording. | Entire cutover and decision closeout. |

# Suggested RC-Day Timeline

| Timebox | Owner | Action | Checkpoint To Pass | Abort / Hold Trigger |
| --- | --- | --- | --- | --- |
| T-90 | PM / Release | Open the release window, confirm attendees, current blockers, and evidence storage location. | All required owners are online and the latest docs are loaded. | Missing owner, missing device pair, or unresolved Sev1 blocker before start. |
| T-75 | iOS / QA | Re-run child script gates and parent build sanity. Confirm the parent scheme still builds and the child repo-managed checks remain green. | Automated child gates stay green and parent build sanity passes. | New regression or failing build before validation starts. |
| T-60 | QA / iOS | Run the final shared paired-device cases still required for RC, especially location, push, lock, and any previously open Sev1 rows. | Every required Sev1 case is PASS or explicitly waived. | Any Sev1 case fails, becomes flaky, or lacks evidence. |
| T-40 | iOS | Create the child Release archive and confirm the documented child archive path still behaves as expected. | Child archive exists and no new archive-time blocker appears. | Archive or signing blocker appears on child build. |
| T-25 | iOS | Create the parent Release archive using the verified parent archive command. | Parent archive completes successfully. | Parent archive fails or produces a new signing/capability blocker. |
| T-15 | Release | Run Organizer validation or equivalent validation review for both archives and capture screenshots. | No new bundle, privacy, capability, extension, or validation blocker remains. | Any validation blocker remains unresolved. |
| T-10 | Release / QA | Assemble the evidence pack and confirm diagnostics exports, screenshots, archive paths, and validation results are attached. | Evidence pack is complete enough for sign-off review. | Evidence is incomplete or cannot be traced to the exact build under review. |
| T-05 | PM / Leads | Review the RC checklist and collect final sign-off from PM, iOS, backend, QA, and release owner. | All required approvers sign the same evidence set. | A required approver refuses, defers, or asks for new evidence. |
| T+00 | PM / Release | Record the decision as GO, HOLD, or NO-GO and announce it to the team. | A single decision is documented with timestamp and owner. | Decision is unclear, split, or missing owner accountability. |
| T+15 | Release | If GO, preserve artifacts and proceed with the planned promotion step. If HOLD/NO-GO, execute rollback handling and publish a fresh handoff. | Release state is stable and the next action is explicit. | Artifacts missing, rollback unclear, or next shift lacks a clean handoff. |

# Required Checkpoints

Checkpoint 1: combined blocker tracker has no unresolved Sev1 blocker at the moment the window starts.

Checkpoint 2: paired-device evidence covers every required Sev1 validation row.

Checkpoint 3: both archives exist and validation evidence is attached.

Checkpoint 4: all named approvers review the same evidence set before signing.

# Immediate Hold Conditions

Location, push, lock, or bind behavior differs between the evidence pack and the live rerun.

Backend contract answers remain ambiguous for bind policy, websocket policy, or push semantics.

Any archive or Organizer validation step introduces a new blocker.

The release window loses its required owner coverage and no fallback owner is available.

# Communication Moments

| Moment | Audience | What To Send |
| --- | --- | --- |
| Window open | PM, iOS, QA, backend, release owner | Current blocker state, active build IDs, device pair, and target decision time. |
| Hold condition hit | All release participants | Exact failing checkpoint, owning blocker ID, and next recovery step. |
| GO decision | All release participants and downstream stakeholders | Build IDs, archive timestamps, approval set, and next promotion step. |
| HOLD / NO-GO decision | All release participants and downstream stakeholders | Blocking issue, owner, next checkpoint, and rollback / handoff path. |

# Artifacts To Preserve Before Closing The Window

Final RC checklist with sign-off status.

Current blocker tracker snapshot.

Evidence pack or evidence-pack template filled for the actual RC.

Archive timestamps and paths for both apps.

Organizer or validation screenshots for both apps.

Fresh handoff note if the decision is not GO.

Repo inputs used: combined RC checklist, blocker tracker, cutover runbook, handoff template, and verified archive state reviewed on 2026-04-08.