# Smart Oila Parent + Child Release Dependency Matrix

Date: 2026-04-08

Purpose: map the critical parent, child, backend, device, entitlement, and approval dependencies that determine whether the combined release can advance from HOLD to GO

Current posture: the child app is near RC from repo-managed gates, the parent app is buildable and archivable, and the combined release remains HOLD because several critical flows depend on shared real-device validation, backend confirmation, parent release hardening, and complete release evidence. This matrix connects those dependencies to owners, failure signals, and closure proof.

# Dependency Rules

A dependency is only considered closed when its proof is attached to the current evidence pack and reflected in the checkpoint scorecard.

If a shared dependency fails, the release state applies to both apps until the impact is explicitly bounded.

Dependencies that require physical devices, entitlements, or backend answers cannot be inferred from simulator-only or code-only checks.

A waiver can narrow residual risk, but it cannot replace missing proof for a non-waivable dependency.

# Cross-System Dependency Matrix

| Dependency | Status | Depends On | Failure Signal | Closure Evidence | Owner |
| --- | --- | --- | --- | --- | --- |
| Parent build and archive | Green | Parent scheme and signing, release configuration, archive command, evidence pack linkage | Parent build cannot be traced or reviewed at the final checkpoint. | Local Release archive proof, build identity, final archive path in evidence pack. | Parent iOS owner |
| Child build, extensions, and entitlements | Green | Child app target, Screen Time extensions, signing, release archive proof | Child binary or extension state is unclear at sign-off time. | Child archive proof plus entitlement and extension validation artifacts. | Child iOS owner |
| Parent-child bind and session integrity | Yellow | Real device pair, current sessions, backend environment stability, validation run order | Pairing breaks, stale session state, or inconsistent account linkage between apps. | Fresh device-pair run with logs, screenshots, and blocker status update. | QA owner + backend owner |
| Push delivery and notification routing | Red | APNs entitlements, backend push pipeline, live devices, active sessions, environment match | Push arrives late, to the wrong app state, or not at all on current builds. | Live push evidence on the target environment for both parent and child contexts. | Backend owner + QA owner |
| Background location and geofence behavior | Red | Location permissions, backend environment, device motion, background execution timing | Location events or geofence updates do not converge between device and backend state. | Real-device geofence and background-location run with preserved timestamps and logs. | QA owner + backend owner |
| App controls and lock enforcement | Red | Screen Time runtime gating, child extensions, app group or shared state, parent control path | Parent action does not produce the expected child-side lock or control behavior. | End-to-end device-pair proof for control issue, receipt, and child enforcement. | Child iOS owner + QA owner |
| Chat, recordings, media, and support flows | Yellow | Backend media or messaging routes, current auth state, device network quality, parent surfaces | Messages, recordings, or media fail to sync cleanly across current app sessions. | Cross-app media and messaging evidence showing acceptable behavior or bounded defect scope. | QA owner |
| SOS, tasks, and critical event propagation | Yellow | Backend event routing, push path, active sessions, real-device proof | Critical event state diverges across apps or lacks timely user-visible confirmation. | End-to-end event proof with logs, screenshots, and timing notes. | QA owner + backend owner |
| Parent release hardening and security posture | Red | Remaining parent release-config debt, secret-handling disposition, PM acceptance if needed | A late security or release-config issue can invalidate the GO call. | Disposition record, mitigation or fix evidence, and if needed an approved waiver entry. | Parent iOS owner + PM owner |
| Evidence pack and final sign-off chain | Red | Current checklist, blocker tracker, ownership matrix, approvals, communications, archive identities | Release state cannot be defended even if engineering work is mostly done. | Complete evidence pack plus explicit GO sign-off from required lanes. | Release owner + PM owner |

# Dependency To Release Gate Mapping

| Release Gate | Critical Dependencies | Gate Opens When | Hold If |
| --- | --- | --- | --- |
| RC validation checkpoint | Bind, push, location, geofence, app controls, critical event propagation | Latest device-pair run closes or bounds all shared behavioral failures. | Any shared device-dependent flow remains unproven or unowned. |
| Backend readiness checkpoint | Push pipeline, location support, environment answer, contract clarifications | Backend owner confirms the active environment and resolves release-critical open questions. | A backend-dependent flow still lacks an approved answer or mitigation. |
| Security and config checkpoint | Parent release hardening and any residual child entitlement risk | Remaining release-config and security concerns are fixed, mitigated, or formally waived. | An unbounded security or release-config issue remains open. |
| Evidence checkpoint | Archive identities, validation evidence, blocker status, decision log, waiver state | The current release story can be proven from artifacts without relying on memory or side chat. | Any GO argument depends on missing screenshots, logs, archive proof, or unsigned approval. |
| Final GO checkpoint | All Red dependencies cleared or formally dispositioned | Required owners can point to proof, current state, and the next cutover action. | One critical dependency still sits in Red or a required approval lane is absent. |

# Watch Items And Immediate Actions

| Watch Item | Why It Is Active Now | Immediate Action | Owner |
| --- | --- | --- | --- |
| Physical device-pair availability | Several highest-risk dependencies cannot close without the actual parent and child devices. | Reserve devices, sequence critical-path cases first, and announce the next checkpoint time before each run. | Release owner |
| Environment drift between validation and release | Push, location, and sync behavior are environment-sensitive and can invalidate prior proof. | Freeze the target environment name and record it in the decision log and communications. | Backend owner |
| Late discovery of parent-side release-config debt | The parent repo still carries release-hardening concerns that can flip a GO call. | Review and disposition the remaining parent hardening items before the final sign-off review. | Parent iOS owner |
| Evidence lag behind actual work | A dependency may be fixed but still appear open if the artifact trail is stale. | Update the evidence pack and checkpoint scorecard in the same cycle as any dependency closure. | QA owner + release owner |
| Mismatch between blocker, waiver, and decision records | Conflicting documents cause incorrect GO or HOLD calls. | Reconcile the blocker tracker, waiver register, decision log, and communications before each checkpoint. | Release owner |

# Usage Rules

Use this matrix with the checkpoint scorecard: the scorecard summarizes state, while this document explains what each state depends on.

If a dependency changes status, update the blocker tracker and communications kit in the same reporting cycle.

Do not mark a dependency Green based only on source review when the dependency explicitly requires live-device or backend proof.

Repo inputs used: combined release plan, real-device validation matrix, RC checklist, blocker tracker, cutover runbook, ownership matrix, checkpoint scorecard, waiver register, and communications kit reviewed on 2026-04-08.