# Smart Oila Kids - 6-Week Roadmap (Repo-Based)

Generated: March 5, 2026

Planning window: Week 1 (March 9-15, 2026) through Week 6 (April 13-19, 2026)

Source basis: current Swift modules, service wiring, CHILD_ONLY_EXTRACTION_SPEC.md, PARENT_CHILD_TESTING.md, and scripts/check_openapi_coverage.py output.

# 1) Current Repo Baseline

Auth is implemented with QR claim + legacy fallback claim endpoint (/upload-v2/device), plus child binding verification.

Root flow is DSN-gated: missing DSN -> Auth, existing DSN -> Main.

Main includes SOS, weekly usage chart, device status snapshot, unread chat/tasks/notifications counters, and pull-to-refresh.

Chat includes history fetch, message send (multipart), websocket receive, local outbox queue, and read-state tracking.

Tasks include awards fetch, change-status action, optimistic queueing for retry, and local cache fallback.

Settings include profile rename, connected device rename/avatar upload/delete, and local cache.

Background services include geo websocket (location + system_info events), device lock polling/overlay, and push inbox/deep-link routing.

App has localization in en/ru/uz and a shared design system (colors, typography, child chrome components).

# 2) Architecture Constraints and Repo-TODO Signals

Platform constraints: SwiftUI app, iOS deployment target 16.0, single iPhone family target.

Scope constraint: child-only app boundaries are documented; parent-only feature families are out of scope.

API/WS constraints: env-driven base URLs with hardcoded defaults and websocket secret path tokening.

Auth constraint: mixed DSN-only and tokenized endpoint behavior is actively handled (401/403/404 fallbacks).

Coverage gap signal: child currently covers 19/85 REST operations and 2/23 websocket routes from OpenAPI coverage audit (run on March 5, 2026).

Integration dependency: parent-child simulator/testing scripts depend on sibling parent repo path on Desktop.

Testing constraint: automated coverage is minimal (script-level unit test only for OpenAPI coverage parser).

Backlog/TODO signal from extraction spec: confirm official child HTTPS base URL, auth/token rules, websocket routes, and finalize unresolved Settings node mapping.

# 3) Milestones

Milestone 1 (Week 1): Scope and API contract freeze for child app parity.

Milestone 2 (Week 2): Auth and session reliability hardening.

Milestone 3 (Week 3): Core engagement reliability (Main + Chat + Tasks).

Milestone 4 (Week 4): Background services and lock/push correctness.

Milestone 5 (Week 5): Settings/device management and localization polish.

Milestone 6 (Week 6): Release candidate stabilization and pilot readiness.

# 4) Week-by-Week Plan

| Week | Focus | Weekly Goals | Deliverables | Dependencies | Risks |
| --- | --- | --- | --- | --- | --- |
| Week 1 Mar 9-15 | Scope + Contract Lock | Lock child-only scope and parity baseline. Run endpoint audit + OpenAPI gap baseline. Resolve Settings mapping ambiguity. | Approved scope matrix (feature in/out). Contract matrix for Auth/Chat/Tasks/Geo/Lock routes. Prioritized 6-week engineering backlog. | Backend owner confirmations. Figma access for unresolved Settings node. | Risk: contract drift during build. Mitigation: freeze doc + change control. |
| Week 2 Mar 16-22 | Auth + Session Hardening | Harden QR and legacy claim path behavior. Validate DSN verification retries and error states. Stabilize token refresh/session persistence edge cases. | Auth reliability checklist pass. Known error-state UX matrix and expected copy. Session-handling regression checklist. | Valid QR payload corpus. Test credentials for tokenized APIs. | Risk: 401/404 loops and broken onboarding. Mitigation: explicit retry caps + fallback gates. |
| Week 3 Mar 23-29 | Main + Chat + Tasks Reliability | Improve websocket reconnect/outbox replay behavior. Harden unread counters and cross-screen sync. Validate queued task actions and cache replay. | Chat reliability report (delivery/reconnect). Tasks offline-sync validation report. Main dashboard fallback behavior verified. | Stable websocket environment. Push payload samples for chat/tasks events. | Risk: duplicate/out-of-order messages. Mitigation: timestamp/fingerprint guardrails + replay tests. |
| Week 4 Mar 30-Apr 5 | Background + Lock + Push | Validate geo websocket payload cadence in foreground/background. Verify lock overlay correctness from full/global lock endpoints. Test notification deep-links and badge reconciliation. | Background behavior matrix (device/network conditions). Lock-state acceptance checks. Push inbox/deep-link end-to-end test evidence. | APNs test setup. Real device coverage beyond simulators. | Risk: iOS background delivery constraints. Mitigation: fallback polling + monitoring hooks. |
| Week 5 Apr 6-12 | Settings + Polish | Finalize profile/device rename/avatar/delete flows. Close localization and UI consistency gaps. Run regression pass on settings and session clear flows. | Settings regression suite results. Localization QA sheet (en/ru/uz). Design and copy sign-off package. | Backend device-management permissions. Final UX approvals. | Risk: permission mismatches on device mutation endpoints. Mitigation: preflight authorization checks + safe fallbacks. |
| Week 6 Apr 13-19 | Release Readiness | Run parent-child integration scripts and smoke suite. Re-run OpenAPI coverage and verify targeted closure. Stabilize, cut RC, and prepare pilot monitoring. | Release candidate build. Go/no-go checklist with rollback plan. Pilot rollout + post-launch monitoring checklist. | Parent repo availability for integration run. Release sign-off from backend and product. | Risk: late backend changes or integration regressions. Mitigation: freeze window + rollback criteria. |

# 5) Explicit Dependencies

Backend API owner sign-off on child auth/message/awards/lock/geo contracts.

Websocket environment stability (base URL, secret path, and access policy).

Access to parent repository path used by integration scripts (../Smart Oila Parent).

Figma access to finalize unresolved Settings parity mapping.

QA devices and APNs-capable environment for push and background validation.

# 6) Explicit Risk Register

Contract drift risk between legacy and tokenized endpoints while migration is active.

Authentication mode mismatch risk (DSN-only behavior vs token-required routes).

Websocket resilience risk under reconnect/load/network changes.

Background execution risk on iOS for timely location/system_info delivery.

Low automated test coverage risk causing regressions in multi-feature interactions.

# 7) Definition of Done by End of Week 6

Core child flows are reliable in production-like conditions: Auth, Main, Chat, Tasks, Settings, Geo, Lock, Push.

Critical endpoint and websocket paths for child use-cases are validated against OpenAPI and runtime behavior.

Integration scripts and smoke checks pass for parent-child workflow on target simulators/devices.

Release candidate and pilot rollout checklist are complete with clear rollback criteria.